## Prerequisities
Prerequisities
Remote Ubuntu VM (Local VM) | GitLab (saas) | Dockerhub | GKE | Git Hub
Ready | Ready | Ready | Ready | Ready
TF_HTTP_USERNAME | create repo -go-assignment | Repo - rayezcaroll/go-assignment | Create Project | Create Repo - go-deployment
TF_HTTP_PASSWORD | SSH - auth account | PAT | Create Compute Engine API | Deploy keys - Git User SSH Public Key
GITLAB_ACCESS_TOKEN | Variable - DOCKER_KEY |  |  | Deploy keys - ArgoCD Pull SSH Public Key
gcloud auth login --no-launch-browser | Variable - DOCKER_USER
gcloud auth application-default login --no-launch-browser | main - Maintainers / Maintainers (Protected)
Docker User + PAT - docker login
TF State backend - state_backend
To Apply | State Access Token - GITLAB_ACCESS_TOKEN
TF_STATE_NAME
ssh-keygen | GitLab Runner VM (Local VM)
SSH Priv/Pub keys for argocd
configure gitlab-runner
Dir Structure | $ gitlab-runner run
gitlab - go files
k8s - kustomize
argo - Dir for Application / secret
terraform - Dir with .tf files
sshuser - SSH keys for ArgoCD
Linux packages and Alias
git
docker (Completion)
kubectl (Completion)
terraform (Completion)
tree
argocd
kustomize
alias ll = ls -lrth
alias k = kubectl
alias t = terraform
alias - gaa = 'git add .'
alias - gc = 'git commit'
alias - gp = 'git push origin main'

## Documentation
Documentation
Docker Hub
1 | golang | https://hub.docker.com/_/golang
2 | Docker Hub Repo | https://hub.docker.com/repository/docker/rayezcaroll/go-assignment/general
Argocd
1 | argocd cli | https://argo-cd.readthedocs.io/en/stable/cli_installation/
3 | argocd completion | https://argo-cd.readthedocs.io/en/latest/user-guide/commands/argocd_completion/
2 | argocd manifest (non-ha / cluster-admin) | https://raw.githubusercontent.com/argoproj/argo-cd/stable/manifests/install.yaml
3 | Secret and Application | https://argo-cd.readthedocs.io/en/stable/operator-manual/declarative-setup/
4 | Automated Sync Policy | https://argo-cd.readthedocs.io/en/stable/user-guide/auto_sync/
5 | Sync Option | https://argo-cd.readthedocs.io/en/stable/user-guide/sync-options/#respect-ignore-differences-configs
6 | webhooks | https://argo-cd.readthedocs.io/en/stable/operator-manual/webhook/
Kubectl 1.31
1 | kubectl installation | https://v1-31.docs.kubernetes.io/docs/setup/production-environment/tools/kubeadm/install-kubeadm/
2 | kubectl completion | https://kubernetes.io/docs/tasks/tools/install-kubectl-linux/#enable-shell-autocompletion
3 | Deployment | https://kubernetes.io/docs/concepts/workloads/controllers/deployment/
4 | Service | https://kubernetes.io/docs/concepts/services-networking/service/
5 | Secret | https://kubernetes.io/docs/concepts/configuration/secret/
6 | Container Resource Management | https://kubernetes.io/docs/concepts/configuration/manage-resources-containers/
Terraform
1 | terraform installation | https://developer.hashicorp.com/terraform/tutorials/aws-get-started/install-cli#install-terraform
2 | terraform completion | https://developer.hashicorp.com/terraform/cli/commands
Terraform - Google Cloud Platform Provider
| Provider | https://registry.terraform.io/providers/hashicorp/google/latest/docs
| google_project_service | https://registry.terraform.io/providers/hashicorp/google/latest/docs/resources/google_project_service
| google_compute_network | https://registry.terraform.io/providers/hashicorp/google/latest/docs/resources/compute_network.html
| google_compute_route | https://registry.terraform.io/providers/hashicorp/google/latest/docs/resources/compute_route.html
| google_compute_subnetwork | https://registry.terraform.io/providers/hashicorp/google/latest/docs/resources/compute_subnetwork
| google_compute_address | https://registry.terraform.io/providers/hashicorp/google/latest/docs/resources/compute_address.html
| google_compute_router | https://registry.terraform.io/providers/hashicorp/google/latest/docs/resources/compute_router
| google_compute_router_nat | https://registry.terraform.io/providers/hashicorp/google/latest/docs/resources/compute_router_nat
| google_compute_firewall | https://registry.terraform.io/providers/hashicorp/google/latest/docs/resources/compute_firewall
| google_container_cluster | https://registry.terraform.io/providers/hashicorp/google/latest/docs/resources/container_cluster
| google_service_account | https://registry.terraform.io/providers/hashicorp/google/latest/docs/resources/google_service_account
| google_project_iam_member | https://registry.terraform.io/providers/hashicorp/google/latest/docs/resources/google_project_iam
| google_container_node_pool | https://registry.terraform.io/providers/hashicorp/google/latest/docs/resources/container_node_pool
Kustomize
1 | kustomize installation | https://snapcraft.io/install/kustomize/ubuntu
2 | kustomize completion | https://github.com/kubernetes-sigs/kustomize/blob/master/cmd/config/docs/commands/completion.md
3 | kustomization | https://kubectl.docs.kubernetes.io/references/kustomize/kustomization/
Gcloud
1 | gcloud installation | https://docs.cloud.google.com/sdk/docs/install-sdk
2 | gcloud completion | https://docs.cloud.google.com/distributed-cloud/hosted/docs/latest/gdch/resources/gdcloud-auto-completion

## RunBook
Commands for Assignment
1 | Login to GCP and Dockerhub | gcloud auth login --no-launch-browser
gcloud auth application-default login --no-launch-browser
docker login -u <username>
2 | Create GitLab CI | cd 1-gitlab
vim Dockerfile
docker build -t <app-name:version> .
docker run -p 8080:8080 <app-name:version>
docker tag <app-name:version> <username/registry:tag>
docker push <username/registry:tag>
vim .gitlab-ci.yml
3 | Push and Run GitLab CI | ssh -T git@gitlab.com
git init
git config user.name "<username>"
git config user.email "<user@mail>"
git add .
git commit -m "first push"
git branch -M main
git remote add origin git@github.com:<gitlab-user-or-group>/<repo-name>.git
git push -uf origin main
4 | Create VPC and GKE using Terraform IAC | cd 2-terraform
terraform init
terraform validate
terraform plan
terraform apply
5 | Check and Connect cluster | gcloud projects list
gcloud config set project <project-name>
gcloud container cluster list
gcloud container clusters get-credentials <cluster-name> --zone <zone> --project <project>
gcloud compute instances list
6 | Create Kustomize YAML files for assignment | cd 3-k8s/base/
k create deployment go-app -n goapp --image <image-name> --port 8080 --dry-run=client -o yaml > deployment.yaml
k create svc loadbalancer go-service --tcp 8080:8080 --dry-run=client -o yaml > service.yaml
gcloud container clusters get-credentials <cluster-name> --zone <zone> --project <project-name>
k config current-context
k apply -f deployment.yaml
k apply -f service.yaml
vim kustomization.yaml ## Reference to Kustomize Documentation (kustomization)
cd ../overlays/prod/
vim kustomization.yaml ## Reference to Kustomize Documentation (kustomization)
cd ~/3-k8s/
kustomize build overlays/prod
7 | Push Kustomize files to GitHub | cd ~/3-k8s
git init
git config user.name "<username>"
git config user.email "<user@mail>"
git add .
git commit "commit name"
git branch -M main
git remote add origin git@github.com:<github-user>/<repo>.git
git push -u origin main
8 | Install and Configure ArgoCD | k create ns argocd
k apply -n argocd -f https://raw.githubusercontent.com/argoproj/argo-cd/stable/manifests/install.yaml
k get svc -n argocd
k edit svc -n argocd argocd-server ## Change ClusterIP to LoadBalancer
k get svc -n argocd -w
k get secrets -n argocd argocd-initial-admin-secret -o yaml
echo <password> ¦ base64 -d ## Login with initial password and change it.
9 | Create ArgoCD Application + Create secret to point GitHub for Kustomize | cd 4-argo
k create secret generic argo-secret --from-file=sshPrivateKey=/path/to/id_rsa --from-literal=type=git --from-literal=url=https://github.com/<git-username>/<git-repo>.git -n argocd --dry-run=client -o yaml > 4-argo/git-secret.yaml
vim git-secret.yaml ## Add label for repository
vim application.yaml ## Reference to Documentation (Secret and Application / Automated Sync Policy / Sync Option)
k apply -f git-secret.yaml
k apply -f application.yaml
10 | Check GO Application | k get deployment -n goapp
k get pod -n goapp
k get svc -n goapp
11 | Test final result | curl http://<public-lb-ip>:8080/?name=ronaldo
Output should be - "Hello ronaldo"